## Slide 1
SME-QA Hiring Pilot Kickoff Meeting

## Slide 2
In the competitive hiring process, hiring managers often receive certificates of eligibles that may lack qualified applicants to select.
Notes: ^ Summary of the problem this assessment strategy is solving

## Slide 3
PILOT // WHAT WE TESTED

## Slide 4
Proposed timeline
August –September: Find pooled vacancies, interested Hiring Managers, and SMEs
October: Hold 2.5 day job analysis workshop, recruit, and post announcement
November: SMEs conduct resume review and first assessment
December: SMEs conduct second assessment and HR issues certificates
Notes: This is a draft- you can go from posting the job to issuing certs in just 5-6 weeks if you can get a project manager and HR specialist to commit to that timeframe.

## Slide 5
PILOT // Time Commitment
Subject Matter Experts
2 days: Job Analysis Workshop
2 hours: Resume review training and 2 hours for interview training
8 hours: Resume Review over 1 week
Up to 40 hours (over 3 weeks): Interviews with applicants*
*assumes 100-200 applicants/8 SMEs conducting 2 rounds of 1 on 1 interviews
Hiring Manager/Selecting Official
2 days: Job Analysis Workshop
10 hours: Once the Certificate is issued, commit to any additional interviews and selections within two weeks
Notes: Here is breakdown of the time commitment required by SMEs in the process, and the time required by selecting officials.

## Slide 6
Questions?